## Dashboard
Briscola AI - Model Progress Report
Curated report for significant models only. Generated by scripts/build_model_report.py.
Progression curve data
Model | Big holdout vs heuristic_v1 | Training games | H2H big holdout vs predecessor/current best | Cumulative strength index (sum of H2H)
best_a2c | 16.7736 | 1000000 | 0.76442 | 0.764
best_a2c_v3 | 17.2895 | 1000000 | 0.17928 | 0.944
best_a2c_v4 | 17.5019 | 1000000 | 0.35628 | 1.3
best_a2c_v5 | 17.832 | 1000000 | 0.33972 | 1.64
best_a2c_v6 | 18.4015 | 5000000 | 0.45866 | 2.098
best_a2c_v7 | 18.7314 | 5000000 | 2.274 | 4.372
best_a2c_v8 | 17.6067 | 5000000 | 0.893 | 5.265
Current conclusion
best_a2c_v8 is the recommended v0.22.0 .npz policy: encoder v4 (trick-history memory) plus Net2Net widening to hidden 256, trained via two ExIt sparring generations against value-lookahead(v7). It beats best_a2c_v7 head-to-head (+0.89, 100k paired). The value-lookahead runtime agent remains the stronger advanced option.
Quick comparison
Model | Status | Encoder | Training games | Decision
bc_v3 | teacher | v3 |  | Use as BC teacher/anchor for v3 A2C runs.
best_a2c | promoted | v2 | 1000000 | Promoted as v2 best with overkill guard.
best_a2c_v3 | promoted | v3 | 1000000 | Promoted as recommended v3 baseline.
best_a2c_v4 | promoted | v3 | 1000000 | Promoted as recommended local/webapp/cloud model.
best_a2c_v5 | promoted | v3 | 1000000 | Promoted as recommended model for the v0.11.0 release.
best_a2c_v6 | promoted | v3 | 5000000 | Promoted as recommended model for the v0.12.0 release.
best_a2c_v7 | promoted | v3 | 5000000 | Promoted as recommended model for the v0.19.0 release.
best_a2c_v8 | promoted | v4 | 5000000 | Promoted as recommended model for the v0.22.0 release.

## Milestones
order | date | model_id | type | decision | why | evidence | impact | source
1 | 2026-06-08 | best_a2c | promoted | Make v2 A2C with overkill guard the official best. | Good big benchmark strength and guard mitigated poor trump overkill behavior. | Big holdout vs heuristic_v1 +16.77; promotion H2H source kept in benchmarks. | Stable v2 baseline for UI and later v3 comparisons. | data/models/best_a2c.npz + a2c_v2_best_overkill_gap001_1m_seed50_numba
2 | 2026-06-23 | bc_v3 | teacher | Use encoder v3 BC model as teacher/anchor. | Encoder v3 adds public-history and strategic aggregate features without hidden information. | BC v3 metadata: feature_dim 310, 20 epochs. | Provided a stronger and safer anchor for v3 A2C training. | data/models/bc_v3.npz
3 | 2026-06-23 | best_a2c_v3 | promoted | Promote v3 A2C as recommended baseline. | Improved holdout strength and kept overkill under control with runtime guard. | Consolidation: big H2H roughly non-regressive vs best_a2c; holdout vs heuristic_v1 improved. | New default recommended model, v2 best retained for regression. | data/models/best_a2c_v3.npz + PLAN.md
4 | 2026-06-28 | seed301_200k | rejected | Do not promote the 200k league candidate. | The signal was positive but too small, and heuristic_v1 quality was weaker than the v3 best. | Big vs best_a2c_v3 +0.12/+0.13; decision-quality +16.91 vs heuristic_v1. | Confirmed that 200k is only a screening run. | benchmarks/experiments/a2c_v3_league_seed301_200k_numba/
5 | 2026-06-28 | seed302_200k_conservative | rejected | Do not promote the conservative 200k variant. | It did not beat best_a2c_v3 on the medium screen. | Medium vs best_a2c_v3 -0.12/+0.05. | Avoided spending on a big benchmark for a weak candidate. | benchmarks/experiments/a2c_v3_league_seed302_200k_conservative_numba/
6 | 2026-06-28 | best_a2c_v4 | promoted | Promote v4 as the recommended local/webapp/cloud model. | It beats best_a2c_v3 head-to-head and does not regress against heuristic_v1. | Big vs best_a2c_v3 +0.45/+0.36; big vs heuristic_v1 +17.43/+17.50. | Frontend/server/cloud default now points to v4 via release asset provisioning. | data/models/best_a2c_v4.npz + a2c_v3_league_seed301_1m_numba
7 | 2026-06-28 | best_a2c_v5 | promoted | Promote v5 as the recommended model for v0.11.0. | It beats best_a2c_v4 head-to-head and improves the heuristic_v1 holdout without material quality regressions. | Big vs best_a2c_v4 +0.34; big vs heuristic_v1 +17.83; decision-quality +18.00, overkill 0.0%, waste 0.07%. | Frontend/server default now points to v5; cloud rollout needs the v0.11.0 asset URL in env. | data/models/best_a2c_v5.npz + a2c_v5_seed401_1m_numba
8 | 2026-06-28 | best_a2c_v6 | promoted | Promote v6 as the recommended model for v0.12.0. | The 1M/3M/5M scaling curve improved monotonically, and the 5M checkpoint beat best_a2c_v5 on both standard and holdout suites without quality regressions. | 5M big vs best_a2c_v5 +0.46; holdout big vs best_a2c_v5 +0.46; big vs heuristic_v1 +18.40; decision-quality +18.58, overkill 0.0%, waste 0.07%. | Frontend/server default now points to v6; cloud rollout needs the v0.12.0 asset URL in env. | data/models/best_a2c_v6.npz + a2c_v6_scaling_seed501_5m_numba
9 | 2026-06-29 | best_a2c_v6 | runtime_default | Make v6 + exact endgame solver the default UI opponent for v0.13.0. | The solver is exact, anti-cheat, and effectively free at runtime; it preserves v6 during the game and improves the fully-known endgame instead of trying to distill solver behavior into the network. | control_solver(v6) / bc_model_hybrid_endgame equivalence; PIMC max_unknown=0 sweep showed roughly +1.3..+1.6 avg diff vs v6. | Runtime default changes to bc_model_hybrid_endgame(best_a2c_v6); model progression chart remains unchanged. | src/briscola_ai/ai/agents/registry.py + PLAN.md
10 | 2026-06-29 | best_a2c_v6 | runtime_option | Expose PIMC(v6, 16x8) as an advanced selectable UI opponent for v0.14.0. | PIMC adds measurable value over v6 + solver, but costs CPU, so it should be testable by humans without replacing the lower-risk default. | PIMC(v6,16x10) beat control_solver(v6) at 2000 games; direct Pareto run found no evidence that 16x10 was stronger than 16x8. | UI can select bc_model_pimc_16x8(best_a2c_v6); default remains bc_model_hybrid_endgame(best_a2c_v6). | src/briscola_ai/ai/agents/registry.py + scripts/evaluate_pimc.py + PLAN.md
11 | 2026-07-01 | best_a2c_v7 | promoted | Promote v7 as the recommended .npz policy for v0.19.0. | A 5M A2C run against the fast Numba value-lookahead opponent produced a policy that beats v6 head-to-head and also improves the v6+solver runtime baseline. | Big holdout vs best_a2c_v6 +2.27; medium candidate+solver vs v6+solver +2.27; big holdout vs heuristic_v1 +18.73. It remains slightly below v6 value-lookahead runtime (-0.64 on 10k), so value-lookahead stays selectable as the advanced option. | Frontend/server/cloud default model moves to best_a2c_v7; value model asset remains unchanged. | data/models/best_a2c_v7.npz + train_a2c fast_numba_determinized value-lookahead screen
12 | 2026-07-03 | best_a2c_v8 | promoted | Promote v8 (encoder v4 + hidden 256) as the recommended .npz policy for v0.22.0. | The ExIt iteration-1/2 arms measured every student-side lever with paired controls: the v4 trick-history features add +0.27 net (first positive runtime evidence of the encoder program), Net2Net capacity adds a marginal +0.18, and the combined chain beats v7 by +0.89. | Big holdout 100k paired CIs: vs best_a2c_v7 +0.89 (CI +0.74..+1.05); vs iter1-v4 +0.18 (CI +0.03..+0.33); vs heuristic_v1 +17.61. Belief-as-policy-input was killed (-0.56 vs its own init): the belief is a deterministic function of the same v4 features, so as policy input it is redundant and gradient-chasing it erodes tuned instinct. | Frontend/server/cloud default model moves to best_a2c_v8 (first v4-encoder, first hidden-256 default); value model asset unchanged. Known nuance: inside value-lookahead determinized simulations the v4 history block is empty (mild degradation of the advanced opponent's response modeling, not a correctness issue). | data/models/best_a2c_v8.npz + ExIt iteration-1/2 (docs/plans/belief-expert-iteration.md)

## Best Models
order | model_id | role | status | path | label | encoder | feature_dim | training_games | seed | init | opponent_mix | bc_anchor | bc_anchor_beta | guard | progress_big_holdout_vs_h1 | h2h_big_holdout | decision | notes | data_quality
0 | bc_v3 | teacher/anchor | teacher | data/models/bc_v3.npz | BC MLP (epoche 20) | v3 | 310 |  | 0 |  |  |  |  | FALSE |  |  | Use as BC teacher/anchor for v3 A2C runs. | Behavior cloning MLP v3; important as init/anchor, not as official best. | exact
1 | best_a2c | official best | promoted | data/models/best_a2c.npz | A2C v2 overkill gap 1M (best) | v2 | 288 | 1000000 | 50 | data/models/best_a2c.npz | [{"name": "best_a2c", "prob": 0.65}, {"name": "greedy_points", "prob": 0.05}, {"name": "heuristic_v1", "prob": 0.05}, {"name": "heuristic_v2", "prob": 0.2}, {"name": "random", "prob": 0.05}] |  | 0 | TRUE | 16.7736 | 0.76442 | Promoted as v2 best with overkill guard. | Strong v2 baseline; remains useful for regression comparisons. | exact
2 | best_a2c_v3 | official best | promoted | data/models/best_a2c_v3.npz | Best A2C v3 (consigliato) | v3 | 310 | 1000000 | 300 | data/models/bc_v3.npz | [{"name": "best_a2c", "prob": 0.4}, {"name": "heuristic_v1", "prob": 0.2}, {"name": "heuristic_v2", "prob": 0.3}, {"name": "random", "prob": 0.1}] | data/models/bc_v3.npz | 0.01 | TRUE | 17.2895 | 0.17928 | Promoted as recommended v3 baseline. | Encoder v3, BC/A2C v3 pipeline, guard enabled for runtime/UI. | exact
3 | best_a2c_v4 | official best | promoted | data/models/best_a2c_v4.npz | Best A2C v4 (league v3 1M) | v3 | 310 | 1000000 | 301 | data/models/best_a2c_v3.npz | [{"name": "bc_model", "prob": 0.4}, {"name": "heuristic_v1", "prob": 0.2}, {"name": "heuristic_v2", "prob": 0.3}, {"name": "random", "prob": 0.1}] | data/models/bc_v3.npz | 0.01 | TRUE | 17.5019 | 0.35628 | Promoted as recommended local/webapp/cloud model. | League v3 1M run warm-started from best_a2c_v3 with best_a2c_v3 in the opponent mix. | exact
4 | best_a2c_v5 | official best | promoted | data/models/best_a2c_v5.npz | A2C shaped 1.0M game | v3 | 310 | 1000000 | 401 | data/models/best_a2c_v4.npz | [{"name": "bc_model", "prob": 0.4}, {"name": "heuristic_v1", "prob": 0.2}, {"name": "heuristic_v2", "prob": 0.3}, {"name": "random", "prob": 0.1}] | data/models/bc_v3.npz | 0.01 | TRUE | 17.832 | 0.33972 | Promoted as recommended model for the v0.11.0 release. | League v5 1M run warm-started from best_a2c_v4 with best_a2c_v4 in the opponent mix. | exact
5 | best_a2c_v6 | official best | promoted | data/models/best_a2c_v6.npz | Best A2C v6 (league v5 5M) | v3 | 310 | 5000000 | 501 | data/models/best_a2c_v5.npz | [{"name": "bc_model", "prob": 0.4}, {"name": "heuristic_v1", "prob": 0.2}, {"name": "heuristic_v2", "prob": 0.3}, {"name": "random", "prob": 0.1}] | data/models/bc_v3.npz | 0.01 | TRUE | 18.4015 | 0.45866 | Promoted as recommended model for the v0.12.0 release. | Scaling v6 5M run warm-started from best_a2c_v5 with best_a2c_v5 in the opponent mix. | exact
6 | best_a2c_v7 | official best | promoted | data/models/best_a2c_v7.npz | Best A2C v7 (value-lookahead 5M) | v3 | 310 | 5000000 | 20260701 | data/models/best_a2c_v6.npz |  |  | 0 | TRUE | 18.7314 | 2.274 | Promoted as recommended model for the v0.19.0 release. | 5M A2C run warm-started from best_a2c_v6 against the fast Numba value-lookahead opponent. It becomes the default .npz policy; value-lookahead remains the stronger runtime option. | exact
7 | best_a2c_v8 | official best | promoted | data/models/best_a2c_v8.npz | Best A2C v8 (v4 + net2net 256, 10M) | v4 | 369 | 5000000 | 20260715 | data/models/exit_iter2_seed_v4_h256.npz |  |  | 0 | TRUE | 17.6067 | 0.893 | Promoted as recommended model for the v0.22.0 release. | Encoder v4 (trick-history features) + Net2Net widening to hidden 256. Chain: warm-start from best_a2c_v7 (v4 zero-pad), 5M A2C games vs value-lookahead(v7), widening 128->256, 5M more games. Beats best_a2c_v7 head-to-head (+0.89, CI +0.74..+1.05, 100k paired); the lower score vs heuristic_v1 relative to v7 (17.61 vs 18.73) reflects style non-transitivity, not regression. | exact

## Promotion Evidence
model_id | label | benchmark | engine | suite | opponent | avg_diff | wins_model | wins_opponent | draws | eval_games | source | data_quality
best_a2c | Best A2C v2 | big | numba | standard | heuristic_v1 | 16.6649 | 71148 | 26527 | 2325 | 100000 | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/matrix_big.json | exact
best_a2c | Best A2C v2 | big | numba | standard | random | 46.6717 | 91831 | 7355 | 814 | 100000 | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/matrix_big.json | exact
best_a2c | Best A2C v2 | big | numba | standard | greedy_points | 43.182 | 90159 | 8871 | 970 | 100000 | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/matrix_big.json | exact
best_a2c | Best A2C v2 | big | numba | holdout | heuristic_v1 | 16.7736 | 71351 | 26356 | 2293 | 100000 | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/matrix_big.json | exact
best_a2c | Best A2C v2 | big | numba | holdout | random | 46.3622 | 91446 | 7725 | 829 | 100000 | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/matrix_big.json | exact
best_a2c | Best A2C v2 | big | numba | holdout | greedy_points | 42.9007 | 89929 | 9124 | 947 | 100000 | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/matrix_big.json | exact
best_a2c | Best A2C v2 | big | numba | standard | previous_best_v2 | 0.76442 | 49800 | 47369 | 2831 | 100000 | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/head_to_head_best_a2c_v2_big_numba.json | exact
best_a2c_v3 | Best A2C v3 | big | numba | standard | heuristic_v1 | 17.0696 | 71470 | 26209 | 2321 | 100000 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/baseline_best_a2c_v3_big_vs_heuristic_v1_numba.json | exact
best_a2c_v3 | Best A2C v3 | big | numba | holdout | heuristic_v1 | 17.2879 | 71801 | 25948 | 2251 | 100000 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/baseline_best_a2c_v3_big_vs_heuristic_v1_numba.json | exact
best_a2c_v3 | Best A2C v3 | big | numba | standard | best_a2c.npz | 0.00814 | 48433 | 48683 | 2884 | 100000 | benchmarks/experiments/best_a2c_v3_vs_best_a2c_2026-06-28_big_numba.json | exact
best_a2c_v3 | Best A2C v3 | big | numba | holdout | best_a2c.npz | 0.18258 | 48741 | 48339 | 2920 | 100000 | benchmarks/experiments/best_a2c_v3_vs_best_a2c_2026-06-28_big_numba.json | exact
best_a2c_v4 | Best A2C v4 | big | numba | standard | heuristic_v1 | 17.4348 | 71868 | 25833 | 2299 | 100000 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/eval_big_vs_heuristic_v1_numba.json | exact
best_a2c_v4 | Best A2C v4 | big | numba | holdout | heuristic_v1 | 17.5019 | 72128 | 25687 | 2185 | 100000 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/eval_big_vs_heuristic_v1_numba.json | exact
best_a2c_v4 | Best A2C v4 | big | numba | standard | best_a2c_v3.npz | 0.44858 | 49204 | 47847 | 2949 | 100000 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/head_to_head_best_a2c_v3_big_numba.json | exact
best_a2c_v4 | Best A2C v4 | big | numba | holdout | best_a2c_v3.npz | 0.35628 | 49170 | 47848 | 2982 | 100000 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/head_to_head_best_a2c_v3_big_numba.json | exact
best_a2c_v5 | Best A2C v5 | big | numba | standard | heuristic_v1 | 17.832 | 72432 | 25279 | 2289 | 100000 | benchmarks/experiments/a2c_v5_seed401_1m_numba/eval_big_vs_heuristic_v1_numba.json | exact
best_a2c_v5 | Best A2C v5 | big | numba | standard | best_a2c_v4 | 0.33972 | 49100 | 47967 | 2933 | 100000 | benchmarks/experiments/a2c_v5_seed401_1m_numba/head_to_head_best_a2c_v4_big_numba.json | exact
best_a2c_v6 | Best A2C v6 | big | numba | standard | heuristic_v1 | 18.4015 | 73177 | 24557 | 2266 | 100000 | benchmarks/experiments/a2c_v6_scaling_seed501_5m_numba/eval_5m_vs_heuristic_v1_big_numba.json | exact
best_a2c_v6 | Best A2C v6 | big | numba | standard | best_a2c_v5 | 0.46138 | 49334 | 47678 | 2988 | 100000 | benchmarks/experiments/a2c_v6_scaling_seed501_5m_numba/eval_5m_vs_best_a2c_v5_big_numba.json | exact
best_a2c_v6 | Best A2C v6 | big | numba | standard | best_a2c_v5_holdout | 0.45866 | 49237 | 47697 | 3066 | 100000 | benchmarks/experiments/a2c_v6_scaling_seed501_5m_numba/eval_5m_vs_best_a2c_v5_big_holdout_numba.json | exact

## Decision Quality
model_id | label | benchmark | engine | suite | opponent | avg_diff | trump_waste_rate | trump_overkill_rate | trump_overkill_low_rate | eval_games | source | data_quality
best_a2c_v3 | Best A2C v3 | medium | numba | seat_fair | heuristic_v1 | 17.2046 | 0.00080833 | 0 | 0 | 10000 | benchmarks/experiments/best_a2c_v3_decision_quality_vs_heuristic_v1_2026-06-28_medium_numba.json | exact
best_a2c_v4 | Best A2C v4 | medium | numba | seat_fair | heuristic_v1 | 17.623 | 0.00059535 | 0 | 0 | 10000 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/decision_quality_vs_heuristic_v1_medium_numba.json | exact
best_a2c_v5 | Best A2C v5 | big | numba | seat_fair | heuristic_v1 | 17.9963 | 0.00066582 | 0 | 0 | 100000 | benchmarks/experiments/a2c_v5_seed401_1m_numba/decision_quality_vs_heuristic_v1_big_numba.json | exact
best_a2c_v6 | Best A2C v6 | big | numba | seat_fair | heuristic_v1 | 18.5832 | 0.00073197 | 0 | 0 | 100000 | benchmarks/experiments/a2c_v6_scaling_seed501_5m_numba/quality_5m_vs_heuristic_v1_big_numba.json | exact

## Rejected Candidates
candidate | path | training_games | decision | reason | evidence
seed301_200k | benchmarks/experiments/a2c_v3_league_seed301_200k_numba/model.npz | 200000 | not promoted | Positive big head-to-head, but too small and quality vs heuristic_v1 did not clearly improve. | big vs best_a2c_v3 +0.12/+0.13; decision-quality vs heuristic_v1 +16.91.
seed302_200k_conservative | benchmarks/experiments/a2c_v3_league_seed302_200k_conservative_numba/model.npz | 200000 | not promoted | Did not pass the medium filter against best_a2c_v3. | medium vs best_a2c_v3 -0.12/+0.05; vs heuristic_v1 +16.94/+16.95.

## Sources
kind | id | path | data_quality | note
model | bc_v3 | data/models/bc_v3.npz | exact | metadata_json read from .npz
progress_metric | bc_v3 | Not plotted: supervised teacher, not a playing baseline. | not_applicable | source for Dashboard progression score
model | best_a2c | data/models/best_a2c.npz | exact | metadata_json read from .npz
progress_metric | best_a2c | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/matrix_big.json | exact | source for Dashboard progression score
h2h_metric | best_a2c | benchmarks/experiments/a2c_v2_best_overkill_gap001_1m_seed50_numba/head_to_head_best_a2c_v2_big_numba.json | exact | source for head-to-head score
model | best_a2c_v3 | data/models/best_a2c_v3.npz | exact | metadata_json read from .npz
progress_metric | best_a2c_v3 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/baseline_best_a2c_v3_big_vs_heuristic_v1_numba.json | exact | source for Dashboard progression score
h2h_metric | best_a2c_v3 | benchmarks/experiments/best_a2c_v3_vs_best_a2c_2026-06-28_big_numba.json | exact | source for head-to-head score
model | best_a2c_v4 | data/models/best_a2c_v4.npz | exact | metadata_json read from .npz
progress_metric | best_a2c_v4 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/eval_big_vs_heuristic_v1_numba.json | exact | source for Dashboard progression score
h2h_metric | best_a2c_v4 | benchmarks/experiments/a2c_v3_league_seed301_1m_numba/head_to_head_best_a2c_v3_big_numba.json | exact | source for head-to-head score
model | best_a2c_v5 | data/models/best_a2c_v5.npz | exact | metadata_json read from .npz
progress_metric | best_a2c_v5 | benchmarks/experiments/a2c_v5_seed401_1m_numba/eval_big_vs_heuristic_v1_numba.json | exact | source for Dashboard progression score
h2h_metric | best_a2c_v5 | benchmarks/experiments/a2c_v5_seed401_1m_numba/head_to_head_best_a2c_v4_big_numba.json | exact | source for head-to-head score
model | best_a2c_v6 | data/models/best_a2c_v6.npz | exact | metadata_json read from .npz
progress_metric | best_a2c_v6 | benchmarks/experiments/a2c_v6_scaling_seed501_5m_numba/eval_5m_vs_heuristic_v1_big_numba.json | exact | source for Dashboard progression score
h2h_metric | best_a2c_v6 | benchmarks/experiments/a2c_v6_scaling_seed501_5m_numba/eval_5m_vs_best_a2c_v5_big_holdout_numba.json | exact | source for head-to-head score
model | best_a2c_v7 | data/models/best_a2c_v7.npz | exact | metadata_json read from .npz
progress_metric | best_a2c_v7 | data/eval_best_a2c_v7_vs_heuristic_v1_big_holdout_seedrange1000000.json | exact | source for Dashboard progression score
h2h_metric | best_a2c_v7 | data/eval_a2c_vs_value_lookahead_5M_vs_v6_big_holdout_seedrange1000000.json | exact | source for head-to-head score
model | best_a2c_v8 | data/models/best_a2c_v8.npz | exact | metadata_json read from .npz
progress_metric | best_a2c_v8 | benchmarks/experiments/fase3/iter2_h256_vs_heuristic_v1_big.json | exact | source for Dashboard progression score
h2h_metric | best_a2c_v8 | benchmarks/experiments/fase3/iter2_h256_vs_v7_big.json | exact | source for head-to-head score
rejected_candidate | seed301_200k | benchmarks/experiments/a2c_v3_league_seed301_200k_numba/model.npz | manual_summary | big vs best_a2c_v3 +0.12/+0.13; decision-quality vs heuristic_v1 +16.91.
rejected_candidate | seed302_200k_conservative | benchmarks/experiments/a2c_v3_league_seed302_200k_conservative_numba/model.npz | manual_summary | medium vs best_a2c_v3 -0.12/+0.05; vs heuristic_v1 +16.94/+16.95.

## Detail bc_v3
Detail: bc_v3
Key | Value
Role | teacher/anchor
Status | teacher
Path | data/models/bc_v3.npz
Label | BC MLP (epoche 20)
Format | mlp_bc_v1
Encoder | v3
Feature dim | 310
Training games
Seed | 0
Init
Opponent mix
BC anchor
BC anchor beta
Guard anti-overkill | FALSE
Progress score
H2H score
Decision | Use as BC teacher/anchor for v3 A2C runs.
Notes | Behavior cloning MLP v3; important as init/anchor, not as official best.
Decision milestones
Date | Type | Decision | Why | Evidence
2026-06-23 | teacher | Use encoder v3 BC model as teacher/anchor. | Encoder v3 adds public-history and strategic aggregate features without hidden information. | BC v3 metadata: feature_dim 310, 20 epochs.

## Detail best_a2c
Detail: best_a2c
Key | Value
Role | official best
Status | promoted
Path | data/models/best_a2c.npz
Label | A2C v2 overkill gap 1M (best)
Format | mlp_a2c_shaped_v1
Encoder | v2
Feature dim | 288
Training games | 1000000
Seed | 50
Init | data/models/best_a2c.npz
Opponent mix | [{"name": "best_a2c", "prob": 0.65}, {"name": "greedy_points", "prob": 0.05}, {"name": "heuristic_v1", "prob": 0.05}, {"name": "heuristic_v2", "prob": 0.2}, {"name": "random", "prob": 0.05}]
BC anchor
BC anchor beta | 0
Guard anti-overkill | TRUE
Progress score | 16.7736
H2H score | 0.76442
Decision | Promoted as v2 best with overkill guard.
Notes | Strong v2 baseline; remains useful for regression comparisons.
Decision milestones
Date | Type | Decision | Why | Evidence
2026-06-08 | promoted | Make v2 A2C with overkill guard the official best. | Good big benchmark strength and guard mitigated poor trump overkill behavior. | Big holdout vs heuristic_v1 +16.77; promotion H2H source kept in benchmarks.

## Detail best_a2c_v3
Detail: best_a2c_v3
Key | Value
Role | official best
Status | promoted
Path | data/models/best_a2c_v3.npz
Label | Best A2C v3 (consigliato)
Format | mlp_a2c_shaped_v1
Encoder | v3
Feature dim | 310
Training games | 1000000
Seed | 300
Init | data/models/bc_v3.npz
Opponent mix | [{"name": "best_a2c", "prob": 0.4}, {"name": "heuristic_v1", "prob": 0.2}, {"name": "heuristic_v2", "prob": 0.3}, {"name": "random", "prob": 0.1}]
BC anchor | data/models/bc_v3.npz
BC anchor beta | 0.01
Guard anti-overkill | TRUE
Progress score | 17.2895
H2H score | 0.17928
Decision | Promoted as recommended v3 baseline.
Notes | Encoder v3, BC/A2C v3 pipeline, guard enabled for runtime/UI.
Decision milestones
Date | Type | Decision | Why | Evidence
2026-06-23 | promoted | Promote v3 A2C as recommended baseline. | Improved holdout strength and kept overkill under control with runtime guard. | Consolidation: big H2H roughly non-regressive vs best_a2c; holdout vs heuristic_v1 improved.

## Detail best_a2c_v4
Detail: best_a2c_v4
Key | Value
Role | official best
Status | promoted
Path | data/models/best_a2c_v4.npz
Label | Best A2C v4 (league v3 1M)
Format | mlp_a2c_shaped_v1
Encoder | v3
Feature dim | 310
Training games | 1000000
Seed | 301
Init | data/models/best_a2c_v3.npz
Opponent mix | [{"name": "bc_model", "prob": 0.4}, {"name": "heuristic_v1", "prob": 0.2}, {"name": "heuristic_v2", "prob": 0.3}, {"name": "random", "prob": 0.1}]
BC anchor | data/models/bc_v3.npz
BC anchor beta | 0.01
Guard anti-overkill | TRUE
Progress score | 17.5019
H2H score | 0.35628
Decision | Promoted as recommended local/webapp/cloud model.
Notes | League v3 1M run warm-started from best_a2c_v3 with best_a2c_v3 in the opponent mix.
Decision milestones
Date | Type | Decision | Why | Evidence
2026-06-28 | promoted | Promote v4 as the recommended local/webapp/cloud model. | It beats best_a2c_v3 head-to-head and does not regress against heuristic_v1. | Big vs best_a2c_v3 +0.45/+0.36; big vs heuristic_v1 +17.43/+17.50.

## Detail best_a2c_v5
Detail: best_a2c_v5
Key | Value
Role | official best
Status | promoted
Path | data/models/best_a2c_v5.npz
Label | A2C shaped 1.0M game
Format | mlp_a2c_shaped_v1
Encoder | v3
Feature dim | 310
Training games | 1000000
Seed | 401
Init | data/models/best_a2c_v4.npz
Opponent mix | [{"name": "bc_model", "prob": 0.4}, {"name": "heuristic_v1", "prob": 0.2}, {"name": "heuristic_v2", "prob": 0.3}, {"name": "random", "prob": 0.1}]
BC anchor | data/models/bc_v3.npz
BC anchor beta | 0.01
Guard anti-overkill | TRUE
Progress score | 17.832
H2H score | 0.33972
Decision | Promoted as recommended model for the v0.11.0 release.
Notes | League v5 1M run warm-started from best_a2c_v4 with best_a2c_v4 in the opponent mix.
Decision milestones
Date | Type | Decision | Why | Evidence
2026-06-28 | promoted | Promote v5 as the recommended model for v0.11.0. | It beats best_a2c_v4 head-to-head and improves the heuristic_v1 holdout without material quality regressions. | Big vs best_a2c_v4 +0.34; big vs heuristic_v1 +17.83; decision-quality +18.00, overkill 0.0%, waste 0.07%.

## Detail best_a2c_v6
Detail: best_a2c_v6
Key | Value
Role | official best
Status | promoted
Path | data/models/best_a2c_v6.npz
Label | Best A2C v6 (league v5 5M)
Format | mlp_a2c_shaped_v1
Encoder | v3
Feature dim | 310
Training games | 5000000
Seed | 501
Init | data/models/best_a2c_v5.npz
Opponent mix | [{"name": "bc_model", "prob": 0.4}, {"name": "heuristic_v1", "prob": 0.2}, {"name": "heuristic_v2", "prob": 0.3}, {"name": "random", "prob": 0.1}]
BC anchor | data/models/bc_v3.npz
BC anchor beta | 0.01
Guard anti-overkill | TRUE
Progress score | 18.4015
H2H score | 0.45866
Decision | Promoted as recommended model for the v0.12.0 release.
Notes | Scaling v6 5M run warm-started from best_a2c_v5 with best_a2c_v5 in the opponent mix.
Decision milestones
Date | Type | Decision | Why | Evidence
2026-06-28 | promoted | Promote v6 as the recommended model for v0.12.0. | The 1M/3M/5M scaling curve improved monotonically, and the 5M checkpoint beat best_a2c_v5 on both standard and holdout suites without quality regressions. | 5M big vs best_a2c_v5 +0.46; holdout big vs best_a2c_v5 +0.46; big vs heuristic_v1 +18.40; decision-quality +18.58, overkill 0.0%, waste 0.07%.
2026-06-29 | runtime_default | Make v6 + exact endgame solver the default UI opponent for v0.13.0. | The solver is exact, anti-cheat, and effectively free at runtime; it preserves v6 during the game and improves the fully-known endgame instead of trying to distill solver behavior into the network. | control_solver(v6) / bc_model_hybrid_endgame equivalence; PIMC max_unknown=0 sweep showed roughly +1.3..+1.6 avg diff vs v6.
2026-06-29 | runtime_option | Expose PIMC(v6, 16x8) as an advanced selectable UI opponent for v0.14.0. | PIMC adds measurable value over v6 + solver, but costs CPU, so it should be testable by humans without replacing the lower-risk default. | PIMC(v6,16x10) beat control_solver(v6) at 2000 games; direct Pareto run found no evidence that 16x10 was stronger than 16x8.

## Detail best_a2c_v7
Detail: best_a2c_v7
Key | Value
Role | official best
Status | promoted
Path | data/models/best_a2c_v7.npz
Label | Best A2C v7 (value-lookahead 5M)
Format | mlp_a2c_shaped_v1
Encoder | v3
Feature dim | 310
Training games | 5000000
Seed | 20260701
Init | data/models/best_a2c_v6.npz
Opponent mix
BC anchor
BC anchor beta | 0
Guard anti-overkill | TRUE
Progress score | 18.7314
H2H score | 2.274
Decision | Promoted as recommended model for the v0.19.0 release.
Notes | 5M A2C run warm-started from best_a2c_v6 against the fast Numba value-lookahead opponent. It becomes the default .npz policy; value-lookahead remains the stronger runtime option.
Decision milestones
Date | Type | Decision | Why | Evidence
2026-07-01 | promoted | Promote v7 as the recommended .npz policy for v0.19.0. | A 5M A2C run against the fast Numba value-lookahead opponent produced a policy that beats v6 head-to-head and also improves the v6+solver runtime baseline. | Big holdout vs best_a2c_v6 +2.27; medium candidate+solver vs v6+solver +2.27; big holdout vs heuristic_v1 +18.73. It remains slightly below v6 value-lookahead runtime (-0.64 on 10k), so value-lookahead stays selectable as the advanced option.

## Detail best_a2c_v8
Detail: best_a2c_v8
Key | Value
Role | official best
Status | promoted
Path | data/models/best_a2c_v8.npz
Label | Best A2C v8 (v4 + net2net 256, 10M)
Format | mlp_a2c_shaped_v1
Encoder | v4
Feature dim | 369
Training games | 5000000
Seed | 20260715
Init | data/models/exit_iter2_seed_v4_h256.npz
Opponent mix
BC anchor
BC anchor beta | 0
Guard anti-overkill | TRUE
Progress score | 17.6067
H2H score | 0.893
Decision | Promoted as recommended model for the v0.22.0 release.
Notes | Encoder v4 (trick-history features) + Net2Net widening to hidden 256. Chain: warm-start from best_a2c_v7 (v4 zero-pad), 5M A2C games vs value-lookahead(v7), widening 128->256, 5M more games. Beats best_a2c_v7 head-to-head (+0.89, CI +0.74..+1.05, 100k paired); the lower score vs heuristic_v1 relative to v7 (17.61 vs 18.73) reflects style non-transitivity, not regression.
Decision milestones
Date | Type | Decision | Why | Evidence
2026-07-03 | promoted | Promote v8 (encoder v4 + hidden 256) as the recommended .npz policy for v0.22.0. | The ExIt iteration-1/2 arms measured every student-side lever with paired controls: the v4 trick-history features add +0.27 net (first positive runtime evidence of the encoder program), Net2Net capacity adds a marginal +0.18, and the combined chain beats v7 by +0.89. | Big holdout 100k paired CIs: vs best_a2c_v7 +0.89 (CI +0.74..+1.05); vs iter1-v4 +0.18 (CI +0.03..+0.33); vs heuristic_v1 +17.61. Belief-as-policy-input was killed (-0.56 vs its own init): the belief is a deterministic function of the same v4 features, so as policy input it is redundant and gradient-chasing it erodes tuned instinct.